## Sheet1
| 2012-05-16 | 2012-05-17 | 2012-05-18 | 2012-05-19 | 2012-05-20 | 2012-05-21 | 2012-05-22 | 2012-05-23 | 2012-05-24 | 2012-05-25 | 2012-05-26 | 2012-05-27 | 2012-05-28 | 2012-05-29 | 2012-05-30 | 2012-05-31 | 2012-06-01 | 2012-06-02 | 2012-06-03 | 2012-06-04 | 2012-06-05 | 2012-06-06 | 2012-06-07 | 2012-06-08 | 2012-06-09 | 2012-06-10 | 2012-06-11
Task1
Task2
Subtask1
Subtask2

## Sheet2
Identifier | Responsible | Code | Start Date | End Date | Time Spent (h) | Percentage Done | Estimated time to complete (h)
L1
..
Identifier | Responsible | Code | Start Date | End Date | Time Spent (h) | Percentage Done | Estimated time to complete (h) | Estimated time left (h)
L2 |  | L2-00 | 2012-04-05 | 2012-04-27 | 103.3 | 52.9 | 175 | 23.8667
UML |  | L2-01 | 2012-04-05 | 2012-04-27 | 55.3 | 92.5 | 160 | 8.7
Class Diagram | Rasmus | L2-01a | 2012-04-05 | 2012-04-27 | 49.3 | 85 | 150 | 8.7
State Machine Diagram | Calle | L2-01b | 2012-04-05 | 2012-04-27 | 6 | 100 | 10 | 0
Architecture 2.0 | Erik | L2-02 | 2012-04-23 | 2012-04-27 | 0 | 1 | 3 | 0
Documentation | Kim | L2-03 | 2012-04-05 | 2012-04-27 | 26 | 65.2 | 12 | 15.1667
R2 |  | L2-03a | 2012-04-02 | 2012-04-09 | 8 | 100 | 2 | 0
R3 |  | L2-03b | 2012-04-09 | 2012-04-16 | 7 | 100 | 2 | 0
R4 |  | L2-03c | 2012-04-16 | 2012-04-23 | 11 | 75 | 2 | 3.6667
R5 |  | L2-03d | 2012-04-24 | 2012-04-30 | 0 | 1 | 2 | 0
L2 Documention |  | L2-03e | 2012-04-05 | 2012-04-27 | 11.5 | 50 | 4 | 11.5
Research |  | L2-04 | 2012-04-05 | 2012-04-27 | 6
Meeting |  | L2-05 | 2012-04-05 | 2012-04-27 | 16
Identifier | Responsible | Code | Start Date | End Date | Time Spent (h) | Percentage Done | Estimated time to complete (h) | Estimated time left (h)
L3 |  | L3-00 | 2012-04-28 | 2012-05-14 |  |  |  | 0
Code |  | L3-01 | 2012-04-18 | 2012-05-14 | 13 |  |  | 0
RenderingComponents |  | L3-01a | 2012-04-18 | 2012-04-28 | 4.5
FrontEndComponents |  | L3-01b | 2012-04-18 | 2012-04-28 | 1.5
Sound |  | L3-01c | 2012-04-18 | 2012-05-07 | 4
Menus |  | L3-01d | 2012-05-07 | 2012-05-11
Collisions |  | L3-01e | 2012-04-28 | 2012-05-07
Game World |  | L3-01f | 2012-04-18 | 2012-05-07 | 3
Player input |  | L3-01g | 2012-04-28 | 2012-05-04
AI |  | L3-01h | 2012-04-28 | 2012-05-07
High Score |  | L3-01i | 2012-05-07 | 2012-05-14
Pause map |  | L3-01j
Demo |  | L3-02 | 2012-05-07 | 2012-05-14
Documentation |  | L3-03 | 2012-05-01 | 2012-05-14 |  |  |  | 0
R6 |  | L3-03a | 2012-05-01 | 2012-05-07
R7 |  | L3-03b | 2012-05-08 | 2012-05-14
L3 Documentation |  | L3-03c | 2012-05-07 | 2012-05-14

## Sheet3
Week 14 | R2 | [5 empty] | Week 15 | R3 | [5 empty] | Week 16 | R4
|  | Total | [6 empty] | Total | [6 empty] | Total
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0.5 | 2 | 1.5 | 0.5 | 0 | 4.5 | Rasmus | 3 | 0 | 4.1 | 5.6 | 0 | 12.7 | Rasmus | 3.5 | 4 | 5 | 0 | 0 | 12.5
Erik | 0 | 4 | 3 | 0 | 0 | 7 | Erik | 0 | 0 | 3.6 | 4.6 | 0 | 8.2 | Erik | 3.5 | 4 | 5 | 0 | 0 | 12.5
Kim | 0 | 4 | 4.5 | 1 | 1 | 10.5 | Kim | 3 | 0 | 4.1 | 6.1 | 0 | 13.2 | Kim | 3.5 | 5 | 5 | 0 | 0 | 13.5
Calle | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Calle | 3 | 0 | 3.1 | 5.1 | 0 | 11.2 | Calle | 3.5 | 4 | 5 | 0 | 0 | 12.5
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 45.3 | [6 empty] | 51
25.5
|  | Documentation | [6 empty] | Documentation | [6 empty] | Documentation
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0.5 | 0 | 1.5 | 0 | 0 | 2 | Rasmus | 0 | 0 | 0.5 | 1.5 | 0 | 2 | Rasmus | 3.5 | 0 | 1 |  |  | 4.5
Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 1 | 0 | 1 | Erik | 3 | 0 | 1.5 |  |  | 4.5
Kim | 0 | 2 | 3 | 0 | 1 | 6 | Kim | 0 | 0 | 0.5 | 1.5 | 0 | 2 | Kim | 3 | 3.5 | 1.5 |  |  | 8
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0.5 | 1.5 | 0 | 2 | Calle | 3 | 1.5 | 1 |  |  | 5.5
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 7 | [6 empty] | 22.5
8
|  | Architecture | [6 empty] | Architecture | [6 empty] | Architecture
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 2 | 0 | 0 | 0 | 2 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 | 0 |  |  |  | 0
Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 |  |  |  | 0
Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 | 0 |  |  |  | 0
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 |  |  |  | 0
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [6 empty] | 0
2
|  | WBS | [6 empty] | WBS | [6 empty] | WBS
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 | 0 |  |  |  | 0
Erik | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 |  |  |  | 0
Kim | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 | 0 |  |  |  | 0
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 |  |  |  | 0
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [6 empty] | 0
7
|  | UML | [6 empty] | UML | [6 empty] | Class Diagram
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 3 | 0 | 3.6 | 3.6 | 0 | 10.2 | Rasmus |  | 3 |  |  |  | 3
Erik | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Erik | 0 | 0 | 3.6 | 3.6 | 0 | 7.2 | Erik | 0.5 | 3 | 0.5 |  |  | 4
Kim | 0 | 0 |  | 0 | 0 | 0 | Kim | 3 | 0 | 3.6 | 3.6 | 0 | 10.2 | Kim |  | 0 | 0.5 |  |  | 0.5
Calle | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Calle | 3 | 0 | 2.6 | 3.6 | 0 | 9.2 | Calle |  | 0 |  |  |  | 0
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 36.8 | [6 empty] | 7.5
7
|  | Research | [6 empty] | Research | [6 empty] | State Machine
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 0 | 0 | 0.5 | 0 | 0.5 | Rasmus | 0 | 0 | 0 | 0.5 | 0 | 0.5 | Rasmus | 0 | 0 |  |  |  | 0
Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 |  |  |  | 0
Kim | 0 | 0 | 0 | 1 | 0 | 1 | Kim | 0 | 0 | 0 | 1 | 0 | 1 | Kim | 0.5 | 1.5 |  |  |  | 2
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0.5 | 1.5 |  |  |  | 2
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1.5 | [6 empty] | 4
1.5
Research
[15 empty] | Monday | Tuesday | Wednesday | Thursday | Friday
[14 empty] | Rasmus |  | 1 | 1 |  |  | 2
[14 empty] | Erik |  | 1 |  |  |  | 1
[14 empty] | Kim |  | 0 |  |  |  | 0
[14 empty] | Calle |  | 0 |  |  |  | 0
3
Programming
[15 empty] | Monday | Tuesday | Wednesday | Thursday | Friday
[14 empty] | Rasmus | 0 | 0 | 3 |  |  | 3
[14 empty] | Erik | 0 | 0 | 3 |  |  | 3
[14 empty] | Kim | 0 | 0 | 3 |  |  | 3
[14 empty] | Calle | 0 | 1 | 4 |  |  | 5
14