## Detailed Progress
Identifier | Responsible | Code | Start Date | End Date | Time Spent (h) | Percentage Done | Estimated time to complete (h) | Estimated time left (h)
L1
..
Identifier | Responsible | Code | Start Date | End Date | Time Spent (h) | Percentage Done | Estimated time to complete (h) | Estimated time left (h)
L2 |  | L2-00 | 2012-04-05 | 2012-04-27 | 123.1 | 100 | 175 | 0
UML |  | L2-01 | 2012-04-05 | 2012-04-27 | 66.6 | 100 | 160 | 0
Class Diagram | Rasmus | L2-01a | 2012-04-05 | 2012-04-27 | 60.6 | 100 | 150 | 0
State Machine Diagram | Calle | L2-01b | 2012-04-05 | 2012-04-27 | 6 | 100 | 10 | 0
Architecture 2.0 | Erik | L2-02 | 2012-04-23 | 2012-04-27 | 3 | 100 | 3 | 0
Documentation | Kim | L2-03 | 2012-04-05 | 2012-04-27 | 31 | 100 | 12 | 0
R2 |  | L2-03a | 2012-04-02 | 2012-04-09 | 8 | 100 | 2 | 0
R3 |  | L2-03b | 2012-04-09 | 2012-04-16 | 7 | 100 | 2 | 0
R4 |  | L2-03c | 2012-04-16 | 2012-04-23 | 14 | 100 | 2 | 0
R5 |  | L2-03d | 2012-04-24 | 2012-04-30 | 2 | 100 | 2 | 0
L2 Documention |  | L2-03e | 2012-04-05 | 2012-04-27 | 17.5 | 100 | 4 | 0
Research |  | L2-04 | 2012-04-05 | 2012-04-27 | 6.5
Meeting |  | L2-05 | 2012-04-05 | 2012-04-27 | 16
Identifier | Responsible | Code | Start Date | End Date | Time Spent (h) | Percentage Done | Estimated time to complete (h) | Estimated time left (h)
L3 |  | L3-00 | 2012-04-28 | 2012-05-14 | 131.5 | 94.15 | 166.5 | 25.8584
Code |  | L3-01 | 2012-04-18 | 2012-05-14 | 119.5 | 76.6 | 148.5 | 25.8584
FrontEndComponents | Kim | L3-01b | 2012-04-18 | 2012-04-28 | 4.5 | 95 | 4.5 | 0.23684
Camera | Rasmus | L3-01c | 2012-04-18 | 2012-04-28 | 9 | 95 | 1.5 | 0.47368
RenderingComponents | Erik | L3-01a | 2012-04-18 | 2012-05-02 | 22.5 | 95 | 32.5 | 1.1842
Sound | Calle | L3-01d | 2012-04-18 | 2012-05-07 | 9 | 95 | 10 | 0.47368
Game World | Kim | L3-01e | 2012-04-18 | 2012-05-07 | 39.5 | 75 | 30 | 13.1667
Player input | Calle | L3-01f | 2012-04-28 | 2012-05-04 | 2 | 95 | 5 | 0.10526
AI | Rasmus | L3-01g | 2012-04-28 | 2012-05-07 | 15 | 95 | 20 | 0.78947
Collisions | Erik | L3-01h | 2012-04-28 | 2012-05-07 | 3 | 50 | 25 | 3
Menus | Kim | L3-01j | 2012-05-07 | 2012-05-11 | 0 | 1 | 5 | 0
GameScreen | Rasmus | L3-01i | 2012-05-07 | 2012-05-14 | 15 | 70 | 15 | 6.4286
Demo | Erik | L3-02 | 2012-05-10 | 2012-05-14 | 2 | 100 | 4 | 0
Documentation | Kim | L3-03 | 2012-05-01 | 2012-05-14 | 5 | 100 | 8 | 0
R6 |  | L3-03a | 2012-05-01 | 2012-05-07 | 3 | 100 | 4 | 0
R7 |  | L3-03b | 2012-05-08 | 2012-05-14 | 2 | 100 | 4 | 0
State Machine Diagram | Rasmus | L3-04 | 2012-05-07 | 2012-05-14 | 1 | 100 | 0 | 0
Research |  | L3-05 |  |  | 2 | 100
Meeting |  | L3-06 |  |  | 2 | 100 | 6
Identifier | Responsible | Code | Start Date | End Date | Time Spent (h) | Percentage Done | Estimated time to complete (h) | Estimated time left (h)
L4 |  | L4-00 | 2012-05-14 | 2012-05-28 | 6 | 5.15 | 145 | 172
Post Mortem |  | L4-01 | 2012-05-14 | 2012-05-25 | 2 | 20.75 | 105 | 0.5
Update Architecture | Erik | L4-01a | 2012-05-14 | 2012-05-21 | 2 | 80 | 20 | 0.5
Update UML | Andreas | L4-01b | 2012-05-14 | 2012-05-21 | 0 | 1 | 30 | 0
Team Evaluation | Calle | L4-01c | 2012-05-21 | 2012-05-25 | 0 | 1 | 25 | 0
Project Summary | Rasmus | L4-01d | 2012-05-21 | 2012-05-25 | 0 | 1 | 30 | 0
Documentation | Kim | L4-02 | 2012-05-14 | 2012-05-25 | 3.5 | 2 | 10 | 171.5
Research |  | L4-03 | 2012-05-14 | 2012-05-28 | 0 | 1 | 5 | 0
Meetings |  | L4-04 | 2012-05-14 | 2012-05-28 | 0.5 | 1 | 5
Oral Presentation | Kim | L4-05 | 2012-05-21 | 2012-05-28 | 0 | 1 | 20 | 0

## Weekly Individual Progress
Week 14 | R2 | [5 empty] | Week 15 | R3 | [5 empty] | Week 16 | R4 | [5 empty] | Week 17 | R5 | [5 empty] | Week 18 | R6 | [5 empty] | Week 19 | R7 | [5 empty] | Week 20 | "R8"
|  | Total | [6 empty] | Total | [6 empty] | Total | [6 empty] | Total | [6 empty] | Total | [6 empty] | Total | [6 empty] | Total
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0.5 | 2 | 1.5 | 0.5 | 0 | 4.5 | Rasmus | 3 | 0 | 4.1 | 5.6 | 0 | 12.7 | Rasmus | 3.5 | 4 | 5 | 1.5 | 4 | 18 | Rasmus | 2 | 3 | 0 | 0 | 0 | 5 | Rasmus | 2 | 0 | 3 | 2.5 | 5 | 12.5 | Rasmus | 3 | 3 | 0.5 | 2 | 0 | 8.5 | Rasmus | 1 | 0 | 0 | 0 | 0 | 1
Erik | 0 | 4 | 3 | 0 | 0 | 7 | Erik | 0 | 0 | 3.6 | 4.6 | 0 | 8.2 | Erik | 3.5 | 4 | 5 | 2.5 | 4 | 19 | Erik | 2.5 | 3 | 0 | 0 | 0 | 5.5 | Erik | 3 | 1 | 3 | 3 | 5 | 15 | Erik | 3 | 6 | 2.5 | 0 | 0 | 11.5 | Erik | 1 | 0 | 0 | 0 | 0 | 1
Kim | 0 | 4 | 4.5 | 1 | 1 | 10.5 | Kim | 3 | 0 | 4.1 | 6.1 | 0 | 13.2 | Kim | 3.5 | 5 | 5 | 2.5 | 4 | 20 | Kim | 2.5 | 3 | 0 | 3 | 1 | 9.5 | Kim | 4 | 2 | 3 | 4.5 | 7 | 20.5 | Kim | 4 | 5 | 2.5 | 4.5 | 2 | 18 | Kim | 1 | 0 | 0 | 0 | 0 | 1
Calle | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Calle | 3 | 0 | 3.1 | 5.1 | 0 | 11.2 | Calle | 3.5 | 4 | 5 | 0 | 4.5 | 17 | Calle | 2.3 | 2 | 0 | 0 | 0 | 4.3 | Calle | 3 | 0 | 3 | 3 | 4 | 13 | Calle | 2 | 3 | 2.5 | 3.5 | 0 | 11 | Calle | 1 | 0 | 0 | 0 | 0 | 1
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 45.3 | [6 empty] | 74 | [6 empty] | 24.3 | [6 empty] | 61 | [6 empty] | 49 | [6 empty] | 4
25.5
|  | Documentation | [6 empty] | Documentation | [6 empty] | Documentation | [6 empty] | Documentation | [6 empty] | Documentation | [6 empty] | Documentation | [6 empty] | Documentation
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0.5 | 0 | 1.5 | 0 | 0 | 2 | Rasmus | 0 | 0 | 0.5 | 1.5 | 0 | 2 | Rasmus | 3.5 | 0 | 1 | 0 | 1 | 5.5 | Rasmus |  | 3 |  |  |  | 3 | Rasmus | 0 | 0 | 0 | 0 | 0.5 | 0.5 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 1 |  |  |  |  | 1
Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 1 | 0 | 1 | Erik | 3 | 0 | 1.5 | 0 | 1 | 5.5 | Erik |  | 3 |  |  |  | 3 | Erik | 0 | 0 | 0 | 0 | 0.5 | 0.5 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 1 |  |  |  |  | 1
Kim | 0 | 2 | 3 | 0 | 1 | 6 | Kim | 0 | 0 | 0.5 | 1.5 | 0 | 2 | Kim | 3 | 3.5 | 1.5 | 0 | 1 | 9 | Kim |  | 3 |  |  | 1 | 4 | Kim | 1 | 0 | 0 | 1 | 1.5 | 3.5 | Kim | 0 | 0 | 0 | 1 | 1 | 2 | Kim | 1 |  |  |  |  | 1
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0.5 | 1.5 | 0 | 2 | Calle | 3 | 1.5 | 1 | 0 | 1 | 6.5 | Calle |  | 2 |  |  |  | 2 | Calle | 0 | 0 | 0 | 0 | 0.5 | 0.5 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 1 |  |  |  |  | 1
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 7 | [6 empty] | 26.5 | [6 empty] | 12 | [6 empty] | 5 | [6 empty] | 2 | [6 empty] | 4
8
|  | Architecture | [6 empty] | Architecture | [6 empty] | Architecture | [6 empty] | Architecture | [6 empty] | UML | [6 empty] | UML | [6 empty] | UML
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 2 | 0 | 0 | 0 | 2 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 | 0 |  | 1 | 0 | 1 | Rasmus | [5 empty] | 0 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | [5 empty] | 0
Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 |  | 1 | 0 | 1 | Erik | [5 empty] | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | [5 empty] | 0
Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 | 0 |  | 1 | 0 | 1 | Kim | [5 empty] | 0 | Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 | 0 | 0 | 0 | 1 | 1 | Kim | [5 empty] | 0
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 |  | 0 | 0 | 0 | Calle | [5 empty] | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | [5 empty] | 0
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [6 empty] | 3 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 1 | [6 empty] | 0
2
|  | WBS | [6 empty] | WBS | [6 empty] | WBS | [6 empty] | WBS | [6 empty] | Demo | [6 empty] | Demo | [6 empty] | Post Mortem
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 | 0 |  | 0.5 | 0 | 0.5 | Rasmus | 0 |  |  |  |  | 0 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | [5 empty] | 0
Erik | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 |  | 1.5 | 0 | 1.5 | Erik | [6 empty] | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | [5 empty] | 0
Kim | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 | 0 |  | 1.5 | 0 | 1.5 | Kim | [6 empty] | Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 | 0 | 0 | 1 | 0 | 1 | Kim | [5 empty] | 0
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 |  | 0 | 0 | 0 | Calle | [5 empty] | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 1 | 0 | 1 | Calle | [5 empty] | 0
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [6 empty] | 3.5 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 2 | [6 empty] | 0
7
|  | UML | [6 empty] | UML | [6 empty] | Class Diagram | [6 empty] | Class Diagram | [6 empty] | Progammering | [6 empty] | Progammering | [6 empty] | Oral Presentation
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 3 | 0 | 3.6 | 3.6 | 0 | 10.2 | Rasmus |  | 3 |  | 0 | 1 | 4 | Rasmus | 2 |  |  |  |  | 2 | Rasmus | 2 | 0 | 3 | 2.5 | 4.5 | 12 | Rasmus | 3 | 3 | 0.5 | 2 | 0 | 8.5 | Rasmus | [5 empty] | 0
Erik | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Erik | 0 | 0 | 3.6 | 3.6 | 0 | 7.2 | Erik | 0.5 | 3 | 0.5 | 0 | 1 | 5 | Erik | 2.5 |  |  |  |  | 2.5 | Erik | 3 | 1 | 3 | 3 | 4.5 | 14.5 | Erik | 3 | 6 | 2.5 | 0 | 0 | 11.5 | Erik | [5 empty] | 0
Kim | 0 | 0 |  | 0 | 0 | 0 | Kim | 3 | 0 | 3.6 | 3.6 | 0 | 10.2 | Kim |  | 0 | 0.5 | 0 | 1 | 1.5 | Kim | 2.5 |  |  |  |  | 2.5 | Kim | 3 | 2 | 3 | 3.5 | 5.5 | 17 | Kim | 4 | 5 | 2.5 | 2.5 | 0 | 14 | Kim | [5 empty] | 0
Calle | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Calle | 3 | 0 | 2.6 | 3.6 | 0 | 9.2 | Calle |  | 0 |  | 0 | 1 | 1 | Calle | 2.3 |  |  |  |  | 2.3 | Calle | 3 | 0 | 3 | 3 | 3.5 | 12.5 | Calle | 2 | 3 | 2.5 | 2.5 | 0 | 10 | Calle | [5 empty] | 0
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 36.8 | [6 empty] | 11.5 | [6 empty] | 9.3 | [6 empty] | 56 | [6 empty] | 44 | [6 empty] | 0
7
|  | Research | [6 empty] | Research | [6 empty] | State Machine | [6 empty] | State Machine
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 0 | 0 | 0.5 | 0 | 0.5 | Rasmus | 0 | 0 | 0 | 0.5 | 0 | 0.5 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus
Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik
Kim | 0 | 0 | 0 | 1 | 0 | 1 | Kim | 0 | 0 | 0 | 1 | 0 | 1 | Kim | 0.5 | 1.5 | 0 | 0 | 0 | 2 | Kim
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0.5 | 1.5 | 0 | 0 | 0 | 2 | Calle
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1.5 | [6 empty] | 4 | [6 empty] | 0
1.5
[16 empty] | Research | [6 empty] | Research
[15 empty] | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
[14 empty] | Rasmus |  | 1 | 1 | 0 | 0 | 2 | Rasmus
[14 empty] | Erik |  | 1 | 0 | 0 | 0 | 1 | Erik
[14 empty] | Kim |  | 0 | 0 | 0 | 0 | 0 | Kim
[14 empty] | Calle |  | 0 | 0 | 0 | 0.5 | 0.5 | Calle
[20 empty] | 3.5 | [6 empty] | 0
[16 empty] | Programming | [6 empty] | Programming
[15 empty] | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
[14 empty] | Rasmus | 0 | 0 | 3 | 0 | 2 | 5 | Rasmus
[14 empty] | Erik | 0 | 0 | 3 | 0 | 2 | 5 | Erik
[14 empty] | Kim | 0 | 0 | 3 | 0 | 2 | 5 | Kim |  |  |  | 3 |  | 3
[14 empty] | Calle | 0 | 1 | 4 | 0 | 2 | 7 | Calle
[20 empty] | 22 | [6 empty] | 3

## Percentage Done
Percentage done |  |  |  | Work Hours
| Week 17 | Week 18 | Week 19 |  | Week 17 | Week 18 | Week 19
L3 | 5% | 27% | 94% | L3 | 21 | 82.5 | 131.5
Code | 17.5% | 57.3% | 76.6% | Code | 21 | 77.5 | 119.5
FrontEndComponents | 30% | 95% | 95% | FrontEndComponents | 1.5 | 4.5 | 4.5
Camera | 80% | 95% | 95% | Camera | 0.5 | 4.5 | 9
RenderingComponents | 30% | 95% | 95% | RenderingComponents | 12.5 | 18.5 | 22.5
Sound | 20% | 95% | 95% | Sound | 4 | 6 | 9
Game World | 10% | 50% | 75% | Game World | 2.5 | 27 | 39.5
Player input | 0% | 95% | 95% | Player input | 0 | 2 | 2
AI | 0% | 70% | 95% | AI | 0 | 15 | 15
Collisions | 0% | 0% | 50% | Collisions | 0 | 0 | 3
Menus | 0% | 0% | 0% | Menus | 0 | 0 | 0
GameScreen | 0% | 0% | 70% | GameScreen | 0 | 0 | 15
Demo | 0% | 0% | 100% | Demo | 0 | 0 | 2
Documentation | 0% | 50.5% | 100% | Documentation | 0 | 3 | 5
R6 | 0% | 100% | 100% | R6 | 0 | 3 | 3
R7 | 0% | 0% | 100% | R7 | 0 | 0 | 2
State Machine Diagram | 0% | 0% | 100% | State Machine Diagram | 0 | 0 | 1
Research | 0% | 0% | 100% | Research | 0 | 2 | 2
Meeting | 100% | 100% | 100% | Meeting | 0 | 2 | 2
Percentage done |  |  |  | Work Hours
| Week 20 | Week 21 |  |  | Week 20 | Week 21
L4 |  |  |  | L4
Post Mortem |  |  |  | Post Mortem
Update Architecture |  |  |  | Update Architecture
Update UML |  |  |  | Update UML
Team Evaluation |  |  |  | Team Evaluation
Project Summary |  |  |  | Project Summary
Documentation |  |  |  | Documentation
Research |  |  |  | Research
Meetings |  |  |  | Meetings
Oral Presentation |  |  |  | Oral Presentation