## Sheet1
| 2012-05-16 | 2012-05-17 | 2012-05-18 | 2012-05-19 | 2012-05-20 | 2012-05-21 | 2012-05-22 | 2012-05-23 | 2012-05-24 | 2012-05-25 | 2012-05-26 | 2012-05-27 | 2012-05-28 | 2012-05-29 | 2012-05-30 | 2012-05-31 | 2012-06-01 | 2012-06-02 | 2012-06-03 | 2012-06-04 | 2012-06-05 | 2012-06-06 | 2012-06-07 | 2012-06-08 | 2012-06-09 | 2012-06-10 | 2012-06-11
Task1
Task2
Subtask1
Subtask2

## Sheet2
Identifier | Responsible | Code | Start Date | End Date | Planned time (h) | Time Spent (h) | Percentage Done | Estimated time left
L1
..
Identifier | Responsible | Code | Start Date | End Date | Planned time (h) | Time Spent (h) | Percentage Done | Estimated total time (h) | Estimated time left (h)
L2 |  | L2-00 | 2012-04-05 | 2012-04-27 | 311.1 | 56.3 | 68.3333 | 82.3902 | 26.0902
UML |  | L2-01 | 2012-04-05 | 2012-04-27 | 207.4 | 42.8 | 75 | 57.0667 | 14.2667
Class Diagram | Rasmus | L2-01a | 2012-04-05 | 2012-04-27 | 165.92 | 38.8 | 60 | 64.6667 | 25.8667
State Machine Diagram | Calle | L2-01b | 2012-04-05 | 2012-04-27 | 41.48 | 4 | 30 | 13.3333 | 9.3333
Architecture 2.0 | Erik | L2-02 | 2012-04-23 | 2012-04-27 | 51.85 | 0 | 80 | 0 | 0
Documentation | Kim | L2-03 | 2012-04-05 | 2012-04-27 | 51.85 | 13.5 | 50 | 27 | 13.5
R2 |  |  | 2012-04-02 | 2012-04-09 |  | 8.5 | 100 | 8.5 | 0
R3 |  |  | 2012-04-09 | 2012-04-16 |  | 5 | 100 | 17 | 0
R4 |  |  | 2012-04-16 | 2012-04-23 |  | 0 | 0 | #DIV/0! | #DIV/0!
L2 Documention |  |  | 2012-04-05 | 2012-04-27 |  | 0 | 0 | #DIV/0! | #DIV/0!
L3 |  | L3-00 | 2012-05-28 | 2012-05-14 | 219.6
L4 |  | L4-00 | 2012-05-15 | 2012-05-25 | 164.7

## Sheet3
Week 14 | R2 | [5 empty] | Week 15 | R3 | [5 empty] | Week 16 | R4
|  | Total | [6 empty] | Total | [6 empty] | Total
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0.5 | 2 | 1.5 | 0.5 | 0 | 4.5 | Rasmus | 3 | 0 | 4.1 | 5.6 | 0 | 12.7 | Rasmus | 3.5 | 3 | 0 | 0 | 0 | 6.5
Erik | 0 | 4 | 3 | 0 | 0 | 7 | Erik | 0 | 0 | 3.6 | 4.6 | 0 | 8.2 | Erik | 3.5 | 3 | 0 | 0 | 0 | 6.5
Kim | 0 | 4 | 4.5 | 1 | 1 | 10.5 | Kim | 3 | 0 | 4.1 | 6.1 | 0 | 13.2 | Kim | 3.5 | 3 | 0 | 0 | 0 | 6.5
Calle | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Calle | 3 | 0 | 3.1 | 5.1 | 0 | 11.2 | Calle | 3.5 | 3 | 0 | 0 | 0 | 6.5
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 45.3 | [6 empty] | 26
25.5
|  | Documentation | [6 empty] | Documentation | [6 empty] | Documentation
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0.5 | 0 | 1.5 | 0 | 0 | 2 | Rasmus | 0 | 0 | 0.5 | 1.5 | 0 | 2 | Rasmus | 3.5 |  |  |  |  | 3.5
Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 1 | 0 | 1 | Erik | 3 |  |  |  |  | 3
Kim | 0 | 2 | 3 | 0 | 1 | 6 | Kim | 0 | 0 | 0.5 | 1.5 | 0 | 2 | Kim | 3 | 1.5 |  |  |  | 4.5
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0.5 | 1.5 | 0 | 2 | Calle | 3 | 1.5 |  |  |  | 4.5
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 7 | [6 empty] | 15.5
8
|  | Architecture | [6 empty] | Architecture | [6 empty] | Architecture
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 2 | 0 | 0 | 0 | 2 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 |  |  |  |  | 0
Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 |  |  |  |  | 0
Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 |  |  |  |  | 0
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 |  |  |  |  | 0
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [6 empty] | 0
2
|  | WBS | [6 empty] | WBS | [6 empty] | WBS
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 |  |  |  |  | 0
Erik | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 |  |  |  |  | 0
Kim | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 |  |  |  |  | 0
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 |  |  |  |  | 0
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [6 empty] | 0
7
|  | UML | [6 empty] | UML | [6 empty] | Class Diagram
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 3 | 0 | 3.6 | 3.6 | 0 | 10.2 | Rasmus |  | 3 |  |  |  | 3
Erik | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Erik | 0 | 0 | 3.6 | 3.6 | 0 | 7.2 | Erik | 0.5 | 3 |  |  |  | 3.5
Kim | 0 | 0 |  | 0 | 0 | 0 | Kim | 3 | 0 | 3.6 | 3.6 | 0 | 10.2 | Kim | [5 empty] | 0
Calle | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Calle | 3 | 0 | 2.6 | 3.6 | 0 | 9.2 | Calle | [5 empty] | 0
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 36.8 | [6 empty] | 6.5
7
|  | Research | [6 empty] | Research | [6 empty] | State Machine
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 0 | 0 | 0.5 | 0 | 0.5 | Rasmus | 0 | 0 | 0 | 0.5 | 0 | 0.5 | Rasmus | 0 |  |  |  |  | 0
Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 |  |  |  |  | 0
Kim | 0 | 0 | 0 | 1 | 0 | 1 | Kim | 0 | 0 | 0 | 1 | 0 | 1 | Kim | 0.5 | 1.5 |  |  |  | 2
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0.5 | 1.5 |  |  |  | 2
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1.5 | [6 empty] | 4
1.5
Research
[15 empty] | Monday | Tuesday | Wednesday | Thursday | Friday
[14 empty] | Rasmus | 0 |  |  |  |  | 0
[14 empty] | Erik | 0 |  |  |  |  | 0
[14 empty] | Kim | 0 |  |  |  |  | 0
[14 empty] | Calle | 0 |  |  |  |  | 0
0