## Detailed Progress
Identifier | Responsible | Code | Start Date | End Date | Time Spent (h) | Percentage Done | Estimated time to complete (h) | Estimated time left (h)
L1
..
Identifier | Responsible | Code | Start Date | End Date | Time Spent (h) | Percentage Done | Estimated time to complete (h) | Estimated time left (h)
L2 |  | L2-00 | 2012-04-05 | 2012-04-27 | 123.1 | 100 | 175 | 0
UML |  | L2-01 | 2012-04-05 | 2012-04-27 | 66.6 | 100 | 160 | 0
Class Diagram | Rasmus | L2-01a | 2012-04-05 | 2012-04-27 | 60.6 | 100 | 150 | 0
State Machine Diagram | Calle | L2-01b | 2012-04-05 | 2012-04-27 | 6 | 100 | 10 | 0
Architecture 2.0 | Erik | L2-02 | 2012-04-23 | 2012-04-27 | 3 | 100 | 3 | 0
Documentation | Kim | L2-03 | 2012-04-05 | 2012-04-27 | 31 | 100 | 12 | 0
R2 |  | L2-03a | 2012-04-02 | 2012-04-09 | 8 | 100 | 2 | 0
R3 |  | L2-03b | 2012-04-09 | 2012-04-16 | 7 | 100 | 2 | 0
R4 |  | L2-03c | 2012-04-16 | 2012-04-23 | 14 | 100 | 2 | 0
R5 |  | L2-03d | 2012-04-24 | 2012-04-30 | 2 | 100 | 2 | 0
L2 Documention |  | L2-03e | 2012-04-05 | 2012-04-27 | 17.5 | 100 | 4 | 0
Research |  | L2-04 | 2012-04-05 | 2012-04-27 | 6.5
Meeting |  | L2-05 | 2012-04-05 | 2012-04-27 | 16
Identifier | Responsible | Code | Start Date | End Date | Time Spent (h) | Percentage Done | Estimated time to complete (h) | Estimated time left (h)
L3 |  | L3-00 | 2012-04-28 | 2012-05-14 | 59.5 | 21.825 | 170.5 | 33.49
Code |  | L3-01 | 2012-04-18 | 2012-05-14 | 59 | 55.3 | 148.5 | 32.3233
FrontEndComponents | Kim | L3-01b | 2012-04-18 | 2012-04-28 | 4.5 | 95 | 4.5 | 0.23684
Camera | Rasmus | L3-01c | 2012-04-18 | 2012-04-28 | 4.5 | 95 | 1.5 | 0.23684
RenderingComponents | Erik | L3-01a | 2012-04-18 | 2012-05-02 | 18.5 | 70 | 32.5 | 7.9286
Sound | Calle | L3-01d | 2012-04-18 | 2012-05-07 | 6 | 95 | 10 | 0.31579
Game World | Kim | L3-01e | 2012-04-18 | 2012-05-07 | 17.5 | 50 | 30 | 17.5
Player input | Calle | L3-01f | 2012-04-28 | 2012-05-04 | 2 | 95 | 5 | 0.10526
AI | Rasmus | L3-01g | 2012-04-28 | 2012-05-07 | 6 | 50 | 20 | 6
Collisions | Erik | L3-01h | 2012-04-28 | 2012-05-07 | 0 | 1 | 25 | 0
Menus | Kim | L3-01j | 2012-05-07 | 2012-05-11 | 0 | 1 | 5 | 0
GameScreen | Rasmus | L3-01i | 2012-05-07 | 2012-05-14 | 0 | 1 | 15 | 0
Demo | Erik | L3-02 | 2012-05-10 | 2012-05-14 | 0 | 1 | 4 | 0
Documentation | Kim | L3-03 | 2012-05-01 | 2012-05-14 | 0.5 | 31 | 8 | 1.1667
R6 |  | L3-03a | 2012-05-01 | 2012-05-07 | 0.5 | 30 | 4 | 1.1667
R7 |  | L3-03b | 2012-05-08 | 2012-05-14 | 0 | 1 | 4 | 0
State Machine Diagram | Rasmus | L3-04 | 2012-05-07 | 2012-05-14 | 0 |  | 4
Research |  | L3-05 |  |  | 0
Meeting |  | L3-06 |  |  | 0 |  | 6

## Weekly Individual Progress
Week 14 | R2 | [5 empty] | Week 15 | R3 | [5 empty] | Week 16 | R4 | [5 empty] | Week 17 | R5 | [5 empty] | Week 18 | R6
|  | Total | [6 empty] | Total | [6 empty] | Total | [6 empty] | Total | [6 empty] | Total
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0.5 | 2 | 1.5 | 0.5 | 0 | 4.5 | Rasmus | 3 | 0 | 4.1 | 5.6 | 0 | 12.7 | Rasmus | 3.5 | 4 | 5 | 1.5 | 4 | 18 | Rasmus | 2 | 3 | 0 | 0 | 0 | 5 | Rasmus | 2 | 0 | 3 | 2.5 | 0 | 7.5
Erik | 0 | 4 | 3 | 0 | 0 | 7 | Erik | 0 | 0 | 3.6 | 4.6 | 0 | 8.2 | Erik | 3.5 | 4 | 5 | 2.5 | 4 | 19 | Erik | 2.5 | 3 | 0 | 0 | 0 | 5.5 | Erik | 3 | 1 | 3 | 3 | 0 | 10
Kim | 0 | 4 | 4.5 | 1 | 1 | 10.5 | Kim | 3 | 0 | 4.1 | 6.1 | 0 | 13.2 | Kim | 3.5 | 5 | 5 | 2.5 | 4 | 20 | Kim | 2.5 | 3 | 0 | 3 | 1 | 9.5 | Kim | 4 | 2 | 3 | 3 | 0 | 12
Calle | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Calle | 3 | 0 | 3.1 | 5.1 | 0 | 11.2 | Calle | 3.5 | 4 | 5 | 0 | 4.5 | 17 | Calle | 2.3 | 2 | 0 | 0 | 0 | 4.3 | Calle | 3 | 0 | 3 | 3 | 0 | 9
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 45.3 | [6 empty] | 74 | [6 empty] | 24.3 | [6 empty] | 38.5
25.5
|  | Documentation | [6 empty] | Documentation | [6 empty] | Documentation | [6 empty] | Documentation | [6 empty] | Documentation
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0.5 | 0 | 1.5 | 0 | 0 | 2 | Rasmus | 0 | 0 | 0.5 | 1.5 | 0 | 2 | Rasmus | 3.5 | 0 | 1 | 0 | 1 | 5.5 | Rasmus |  | 3 |  |  |  | 3 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0
Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 1 | 0 | 1 | Erik | 3 | 0 | 1.5 | 0 | 1 | 5.5 | Erik |  | 3 |  |  |  | 3 | Erik | 0 | 0 | 0 | 0 | 0 | 0
Kim | 0 | 2 | 3 | 0 | 1 | 6 | Kim | 0 | 0 | 0.5 | 1.5 | 0 | 2 | Kim | 3 | 3.5 | 1.5 | 0 | 1 | 9 | Kim |  | 3 |  |  | 1 | 4 | Kim | 1 | 0 | 0 | 0 | 0 | 1
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0.5 | 1.5 | 0 | 2 | Calle | 3 | 1.5 | 1 | 0 | 1 | 6.5 | Calle |  | 2 |  |  |  | 2 | Calle | 0 | 0 | 0 | 0 | 0 | 0
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 7 | [6 empty] | 26.5 | [6 empty] | 12 | [6 empty] | 1
8
|  | Architecture | [6 empty] | Architecture | [6 empty] | Architecture | [6 empty] | Architecture | [6 empty] | UML
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 2 | 0 | 0 | 0 | 2 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 | 0 |  | 1 | 0 | 1 | Rasmus | [5 empty] | 0 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0
Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 |  | 1 | 0 | 1 | Erik | [5 empty] | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0
Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 | 0 |  | 1 | 0 | 1 | Kim | [5 empty] | 0 | Kim | 0 | 0 | 0 | 0 | 0 | 0
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 |  | 0 | 0 | 0 | Calle | [5 empty] | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [6 empty] | 3 | [6 empty] | 0 | [6 empty] | 0
2
|  | WBS | [6 empty] | WBS | [6 empty] | WBS | [6 empty] | WBS | [6 empty] | Demo
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 0 | 0 |  | 0.5 | 0 | 0.5 | Rasmus | 0 |  |  |  |  | 0 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0
Erik | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 |  | 1.5 | 0 | 1.5 | Erik | [6 empty] | Erik | 0 | 0 | 0 | 0 | 0 | 0
Kim | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Kim | 0 | 0 | 0 | 0 | 0 | 0 | Kim | 0 | 0 |  | 1.5 | 0 | 1.5 | Kim | [6 empty] | Kim | 0 | 0 | 0 | 0 | 0 | 0
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 |  | 0 | 0 | 0 | Calle | [5 empty] | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [6 empty] | 3.5 | [6 empty] | 0 | [6 empty] | 0
7
|  | UML | [6 empty] | UML | [6 empty] | Class Diagram | [6 empty] | Class Diagram | [6 empty] | Progammering
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus | 3 | 0 | 3.6 | 3.6 | 0 | 10.2 | Rasmus |  | 3 |  | 0 | 1 | 4 | Rasmus | 2 |  |  |  |  | 2 | Rasmus | 2 | 0 | 3 | 2.5 | 0 | 7.5
Erik | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Erik | 0 | 0 | 3.6 | 3.6 | 0 | 7.2 | Erik | 0.5 | 3 | 0.5 | 0 | 1 | 5 | Erik | 2.5 |  |  |  |  | 2.5 | Erik | 3 | 1 | 3 | 3 | 0 | 10
Kim | 0 | 0 |  | 0 | 0 | 0 | Kim | 3 | 0 | 3.6 | 3.6 | 0 | 10.2 | Kim |  | 0 | 0.5 | 0 | 1 | 1.5 | Kim | 2.5 |  |  |  |  | 2.5 | Kim | 3 | 2 | 3 | 3 | 0 | 11
Calle | 0 | 2 | 1.5 | 0 | 0 | 3.5 | Calle | 3 | 0 | 2.6 | 3.6 | 0 | 9.2 | Calle |  | 0 |  | 0 | 1 | 1 | Calle | 2.3 |  |  |  |  | 2.3 | Calle | 3 | 0 | 3 | 3 | 0 | 9
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 36.8 | [6 empty] | 11.5 | [6 empty] | 9.3 | [6 empty] | 37.5
7
|  | Research | [6 empty] | Research | [6 empty] | State Machine | [6 empty] | State Machine
| Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
Rasmus | 0 | 0 | 0 | 0.5 | 0 | 0.5 | Rasmus | 0 | 0 | 0 | 0.5 | 0 | 0.5 | Rasmus | 0 | 0 | 0 | 0 | 0 | 0 | Rasmus
Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik | 0 | 0 | 0 | 0 | 0 | 0 | Erik
Kim | 0 | 0 | 0 | 1 | 0 | 1 | Kim | 0 | 0 | 0 | 1 | 0 | 1 | Kim | 0.5 | 1.5 | 0 | 0 | 0 | 2 | Kim
Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0 | 0 | 0 | 0 | 0 | 0 | Calle | 0.5 | 1.5 | 0 | 0 | 0 | 2 | Calle
Andreas | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1.5 | [6 empty] | 4 | [6 empty] | 0
1.5
[16 empty] | Research | [6 empty] | Research
[15 empty] | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
[14 empty] | Rasmus |  | 1 | 1 | 0 | 0 | 2 | Rasmus
[14 empty] | Erik |  | 1 | 0 | 0 | 0 | 1 | Erik
[14 empty] | Kim |  | 0 | 0 | 0 | 0 | 0 | Kim
[14 empty] | Calle |  | 0 | 0 | 0 | 0.5 | 0.5 | Calle
[20 empty] | 3.5 | [6 empty] | 0
[16 empty] | Programming | [6 empty] | Programming
[15 empty] | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday | Tuesday | Wednesday | Thursday | Friday
[14 empty] | Rasmus | 0 | 0 | 3 | 0 | 2 | 5 | Rasmus
[14 empty] | Erik | 0 | 0 | 3 | 0 | 2 | 5 | Erik
[14 empty] | Kim | 0 | 0 | 3 | 0 | 2 | 5 | Kim |  |  |  | 3 |  | 3
[14 empty] | Calle | 0 | 1 | 4 | 0 | 2 | 7 | Calle
[20 empty] | 22 | [6 empty] | 3

## Percentage Done
Percentage done | [6 empty] | Work Hours
| Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 |  | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22
L3 | [6 empty] | L3 | 21 | bar: Week 17
Code | Week 17: 17.5% | Code | 21
FrontEndComponents | Week 17: 30% | FrontEndComponents | 1.5
Camera | Week 17: 80% | Camera | 0.5
RenderingComponents | Week 17: 30% | RenderingComponents | 12.5
Sound | Week 17: 20% | Sound | 4
Game World | Week 17: 10% | Game World | 2.5
Player input | [6 empty] | Player input | 0 | bar: Week 17
AI | [6 empty] | AI | 0 | bar: Week 17
Collisions | [6 empty] | Collisions | 0 | bar: Week 17
Menus | [6 empty] | Menus | 0 | bar: Week 17
GameScreen | [6 empty] | GameScreen | 0 | bar: Week 17
Demo | [6 empty] | Demo | 0 | bar: Week 17
Documentation | [6 empty] | Documentation | 0 | bar: Week 17
R6 | [6 empty] | R6 | 0 | bar: Week 17
R7 | [6 empty] | R7 | 0 | bar: Week 17
State Machine Diagram | [6 empty] | State Machine Diagram | 0 | bar: Week 17
Research | [6 empty] | Research | 0 | bar: Week 17
Meeting | Week 17: 100% | Meeting | 0